## Task Tracker
TASK TRACKER
Name: | Shah Shikhar |  |  |  | Date: | 26/07/2021
TASK TITLE | STATUS | PRIORITY | START DATE | DUE DATE | PCT OF TASK COMPLETE | COMMENTS | STATUS MENU | PRIORITY MENU
Table fields discussion | ☒ | HIGH | 26th Jul | 26th Jul | 100% | fields and constraints discussion | ☒ | MEDIUM
Design ER Model | ☒ | HIGH | 27th Jul | 29th Jul | 100% | design ER model
Tables Relationship discussion | ☒ | HIGH | 27th Jul | 29th Jul | 100% | Relationship between tables discussion
Export Database Script From EER Model | ☒ | HIGH | 30th Jul | 30th Jul | 100% | Exporting script to create the database |  | LOW
Query Discussion | ☒ | HIGH | 9th Aug | 10th Aug | 100% | Discussion on how to solve the Queries.
work on queries | ☒ | HIGH | 10th Aug | 12th Aug | 100% | Write the queries
Breakdown tables | ☒ | MEDIUM | 12th Aug | 13th Aug | 100% | Breakdown the 2 tables from database
Presenatation | ☒ | MEDIUM | 14th Aug | 14th Aug | 100% | Create presentation based on the queries we performed
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%